## Activity Log - Erin Byrne
Name: | Erin Byrne | Project Group (Name/Number): sw3-group-1
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
7 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Yes | Yes | EXAMPLE
Natalie was the scrum master this week:
| 2023-07-18 | Research in early stages | 1 hour | yes all. | yes | Researching potential projects.
| 2023-07-20 | Research in early stages | 1 hour | yes all. | yes | Natalie found some CFG past presentations on LinkedIn which we looked through to see how people had done it before.
| 2023-07-23 | Research in early stages | 1 hour | yes all. | yes | We did some write ups to put forward our project ideas.
| 2023-07-28 | Research in early stages | 1 hour | no | yes | Catching up on missed meeting in class.
I was scrum master for this week
| 2023-07-31 | Planning Meeting (outside of class) | 30 minutes | Yes | Yes | we all did some research and sent through project proposals. We were interested in creating a website/information hub for students who are CFG sponsored to find job information.
| 2023-08-01 | Research and attempts at creating spotify API | 1.5 hours | yes Pari | yes | completed the research and attempted but was unable to connec the APIs in the end.
| 2023-08-03 | Caught up on a meeting that I missed due to my graduation | 1 hour | no | yes | I read through notes that i had missed due to missing a meeting (during class) that i was unable to attend due to my University graduation ceremony.
| 2023-08-04 | Wrote up classes and methods/attributes. | 1.5 hours | no | yes | I wrote up detailed and extensive classes that i thought might be necessary for our game and thought about why they may be needed
|  | wrote base code for these classes etc. | 1.5 hours | no | yes | i wrote up some base code for all of the classes which I had considered.
|  | I was scrum master for this week | 1.5 hours | no | yes | Added to-dos to our KANBAN and assigned tasks to group members & set up zoom call for next week. I created an extensive plan for days to split work.
| 2023-08-05 | Homework for the group | 30/40 minutes | yes all. | yes | I was responsible for answering question 3.
Eliza was the scrum master this week:
| 2023-08-07 | Planning Meeting (outside of class) | 40 minutes | yes all. | yes | Updated on what we had done and planned for the week ahead.
| 2023-08-11 | Finalising homework | 40 minutes | yes Pari | yes | Checked through homework and finalised it. Pari submitted the final version.
|  | Changed classes to fit our updated game | 30 minutes | yes Natalie | yes | Wrote out new classes - mostly just narrowing down classes and making a few changes.
Parineeta was the scrum master for this week:
| 2023-08-14 | Planning Meeting (outside of class) | 40 minutes | yes all. | yes | Updated on what we had done and planned for the week ahead.
|  | Did some research and practice code on hashing | 30 minutes | yes Pari | yes
| 2023-08-17 | Made code for username | 2.5 hours | no | yes | Wrote the python code for a username to be able to be inserted for the leaderboards.
|  | manipulating SQL dataase | 1 hour | yes Natalie | yes | Tried manipulating the database to figure out how the username would connect.
| 2023-08-19 | Unittests | 2 hours | yes everyone | yes | I got one unittest working but this is in the archives now as it is less relevant.
Sarah was the scrum master this week:
| 2023-08-21 | Catch up meeting with Pari | 20 minutes | yes Pari | yes
|  | Tried out some unittests | 1 hour | yes Eliza and Sarah | yes | I didn't get these unittests working in time.
| 2023-08-22 | Planning Meeting (outside of class) | 45 minutes | yes all. | yes | Updated on what we had done.
| 2023-08-23 | Planning Meeting (outside of class) | 45 minutes | yes all. | yes | "
|  | editing username code and starting to connect username to score | 4 hours | no | yes | lots achieved but still lots of room for growth and improvement on this section
| 2023-08-24 | More work on editing the username and code and trying to get these to connect to score | 3 hours | no | yes
| 2023-08-25 | Planning Meeting (outside of class) and coding together | 2 hours | yes except Natalie was working | yes
|  | Documentation bits | 1.5 hours | yes all. | yes
| 2023-08-26 | changed databse to remove hashing as no longer necessary | 1 hour | no | yes
|  | Review documentation | 1 hour | yes all. | yes
| 2023-08-26 | Showed games to friends and family | 0.5 hours | n/a | Yes | We now have some user acceptance feedback!
| 2023-08-27 | Reviewed complete project report, code files & github repo | 3 hours | n/a | Yes | Proof-read the complete group report
| 2023-08-27 | Group Meeting - Submit Project & Presentation | 0.5 hours | All | Yes | Submit Project & Discuss Presentation
|  |  | Total time: | 40.5 hours

## Activity Log - Eliza Younger
Name: | Eliza Younger | Project Group (Name/Number): sw3-group-1
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
Natalie was the scrum master this week:
Eliza was the scrum master this week:
2 | 2023-07-31 | group meeting | 0.5 | all | yes | assigned tasks for the week and discussed project formation
2 | 2023-07-31 | watched tutorials on how to use the app development software 'Figma' and research on it's viable use for the project. | 2 | no | yes
2 | 2023-07-31 | write up rules for game | 0.75 | no | yes
2 |  | created user interface design in figma | 8 | no | yes
Erin was the scrum master this week:
3 |  | exporting designs into html and css and editing | 9 | no | no
Parineeta was the scrum master for this week:
4 | 2023-08-14 | team meeting | 0.75 | yes | yes | updated everyone on what we'd done
4 | 2023-08-14 | exporting designs into html and css and editing | 7 | no
4 | 2023-08-15 | exporting designs into html and css and editing | 2 | no | yes
4 | 16/08/0223 | editing html and css | 4.5 | no | no
4 | 2023-08-17 | editing html and css | 2
Sarah was the scrum master this week:
5 | 2023-08-21 | group meeting | 2 | yes | yes | meeting to distinguish the week's tasks
5 | 2023-08-22 | worked on unittests and made a README | 5 | no | no
5 | 2023-08-22 | team meeeting to discuss progress after class | 0.75 | yes | yes
5 | 2023-08-23 | finished the README and continued with unittesting | 4 | no | yes
5 | 2023-08-24 | unittests and importing issues | 4 | no | no
5 | 2023-08-25 | integrating code | 3 | no | no
5 | 2023-08-25 | group meeting | 3 | yes, all but natalie | yes
5 | 2023-08-25 | documentation | 2 | no | no
5 | 2023-08-26 | Showed games to friends and family | 0.5 | n/a | Yes | We now have some user acceptance feedback!
5 | 2023-08-27 | Reviewed complete project report, code files & github repo | 3 | n/a | Yes | Proof-read the complete group report
5 | 2023-08-27 | Group Meeting - Submit Project & Presentation | 0.5 | All | Yes | Submit Project & Discuss Presentation
5 | 2023-08-27 | Group Meeting | 0.5 | Natalie, Pari, Sarah, Eliza | yes | edits and file organisation chat
| 2023-08-27 | Group Meeting
|  |  | Total time: | 64.75

## Activity Log - Sarah Power
Name: | Sarah Power | Project Group (Name/Number): sw3-group-1
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
7 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Yes | Yes | EXAMPLE
Natalie was the scrum master this week:
Eliza was the scrum master this week: |  |  | 30 mins | All | Yes | Assigned tasks for the week and discussed project formation
1 | 2023-08-02 | API research | 180 mins | N/A | Yes | Research into possible use of Open AI as an API to generate hit song lyrics
Erin was the scrum master this week:
2 | 2023-08-09 | Drafting Systems Architecture diagram | 120mins | N/A | Yes | Sent to group for feedback
2 | 2023-08-10 | Finalising Systems Architecture diagram | 80mins | N/A | Yes | Implemented group's feedback
2 | 2023-08-12 | Coding clock | 120mins | N/A | Yes | Attempt at coding timing mechanism for the game
Parineeta was the scrum master for this week:
3 | 2023-08-14 | Group meeting | 40 mins | All | Yes | Group catch up
3 | 2023-08-15 | Research into Flask microframework to convert Python to web application | 180 mins | N/A | Yes | Read documentation and watched tutorial videos
3 | 2023-08-16 | Flask research | 120mins | N/A | Yes | Attempt at integrating html with python
3 | 2023-08-17 | Meeting to discuss suitability of Flask vs Kivy as GUI mechanism | 90mins | Eliza | Yes | Decided to refocus on Kivy
3 | 2023-08-17 | Kivy research | 120mins | N/A | Yes | Read documentation and watched tutorial videos
3 | 2023-08-18 | Work on GUI | 120mins | N/A | Yes | Worked on visual presentation on GUI
I (Sarah) was the scrum master this week:
4 | 2023-08-21 | Group meeting | 120 mins | All | Yes | Group catch up and task allocation
4 | 2023-08-22 | Group meeting | 40 mins | All | Yes | Group catch up and task allocation
4 | 2023-08-22 | Coding | 60mins | N/A | Yes | Reorganised Kivy code into screens.
4 | 2023-08-23 | Coding | 90 mins | N/A | Yes | Wrote code for end screen and for 'play again' function
4 | 2023-08-23 | GUI Coding fixes | 60 mins | N/A | Yes | Fixed issue with score not resetting in between new rounds
4 | 2023-08-24 | Scoreboard | 60mins | N/A | Yes | Coded screen for scoreboard
4 | 2023-08-25 | Group meeting | 180 mins | Eliza, Erin, Pari | Yes | Meeting to discuss final steps and sorting out scoreboard
4 | 2023-08-25 | GUI Coding | 120mins | N/A | Yes | Added imagery and colours to GUI start screen and end screen
| 2023-08-26 | Showed games to friends and family | 30mins | n/a | Yes | We now have some user acceptance feedback!
| 2023-08-27 | Reviewed complete project report, code files & github repo | 180mins | n/a | Yes | Proof-read the complete group report
| 2023-08-27 | Group Meeting - Submit Project & Presentation | 30mins | All | Yes | Submit Project & Discuss Presentation
Total time:

## Activity Log - Natalie Hassall
Name: | Natalie Hassall | Project Group (Name/Number): sw3-group-1
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: | Team Members Involved (if applicable) | Completed? | Notes:
7 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Yes | Yes | EXAMPLE
I (Natalie) was the scrum master this week:
1 | 2023-07-19 | LinkedIn research of previous projects | 60 minutes | No | Yes | Shared links with our group
1 | 2023-07-20 | Early research for potential ideas | 120 minutes | No | Yes
1 | 2023-07-23 | Detailed analysis of Eliza's proposal | 80 minutes | Eliza | Yes
1 | 2023-07-26 | Create google drive with all documents added, kanban board, and zoom link for Monday meetings | 30 minutes | No | Yes
1 | 2023-07-27 | Create SWOT analysis following initial team meeting | 20 minutes | No | Yes
Erin was the scrum master this week:
1 | 2023-07-31 | Planning Meeting (outside of class) | 30 minutes | Yes ALL | Yes
1 | 2023-08-02 | Additional meeting to discuss Game Rules | 20 minutes | Yes EY | Yes
1 | 2023-08-03 | Creation of a database and EER diagram | 80 minutes | No | Yes
1 | 2023-08-06 | Connecting to a database, python config files etc | 90 minutes | No | Yes
Eliza was the scrum master this week:
2 | 2023-08-07 | Planning Meeting (outside of class) | 30 minutes
2 | 2023-08-10 | Creation of all designated classes and unittests py scripts needed | 20 minutes | No | Yes
Parineeta was the scrum master for this week:
3 | 2023-08-18 | Create new simplified database and connect to python script, including new functions | 80 minutes | No | No | Need DB for username/password AND file to run the complete game
Sarah was the scrum master this week:
4 | 2023-08-21 | Planning Meeting (outside of class) | 60 minutes | Yes ALL | Yes
4 | 2023-08-21 | Finalise database script and merge into game_manager | 45 minutes | No | No
4 | 2023-08-22 | Planning Meeting (outside of class) | 80 minutes | Yes ALL | Yes
4 | 2023-08-23 | Planning Meeting (outside of class) | 40 minutes | Yes ALL | Yes
4 | 2023-08-23 | Code and database talking, just missing the username | 90 minutes | No | No
4 | 2023-08-25 | Documentation for database and a review of all sections | 60 minutes | No | Yes
4 | 2023-08-26 | Unittest for correct and incorrect answer | 120 minutes | No | Yes
4 | 2023-08-26 | Unittest for timer | 45 minutes | No | No | Inserted into the failed test section
4 | 2023-08-26 | Showed game to family to complete survey | 30 minutes | n/a | Yes | We now have some user acceptance feedback!
4 | 2023-08-27 | Reviewed complete project report, code files & github repo | 180 minutes | n/a | Yes | Proof-read the complete group report
4 | 2023-08-27 | Group Meeting - Submit Project & Presentation | 30 minutes | All | Yes | Submit Project & Discuss Presentation
1440 minutes
|  | Total time: | 24 hours
Total time:

## Activity Log - Parineeta Pai Ga
Name: | Parineeta Pai Galvao De Melo E Souza |  | Project Group (Name/Number): sw3-group-1
This activity log is for you to document your individual contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions, or use this as a way to take notes for your own viewing. This is to be completed individually.
Week: | Date: | Activity/Task: | Time spent on Activity: (Hours) | Team Members Involved (if applicable) | Completed? | Notes:
Natalie was the scrum master this week:
| 2023-07-17 | Early research | 1 | n/a | Yes | Researched simple python programs and games
| 2023-07-19 | Early research | 1 | n/a | Yes | Looked at past CFG projects on LinkedIn
| 2023-07-23 | Early research | 1 | n/a | Yes | Researched creating a learning website, skills needed (html, css, javascript),Database requirements. How we would add more python functionality. For example a code checker.
| 2023-07-26 | Early research | 1 | n/a | Yes | Researched free Apis for a more python based program. Looked at google translate API , a weather API, a capital cities API and Soptify API
| 2023-07-27 | Group meeting - During class | 1 | All, except erin | Yes | Finalised project topic. Decided to go with a music API for a guess the tune style game
Eliza was the scrum master this week:
1 | 2023-07-31 | Group meeting | 0.5 | All | Yes | Assigned tasks for the week and discussed project formation
1 | 2023-07-31 | API research | 3 | n/a | Yes | Looked into API documentation for soundcloud, deezer and spotify. Researched them using google and youtube.
1 | 2023-08-02 | Soundcloud & Deezer APIs | 3 | n/a | No/Yes | Managed to connect to the Deezer/Soundcloud API but was not able to fetch songs
1 | 2023-08-04 | Spotify API - Research, Read documentation and tested connection | 3 | n/a | Yes | Conected to spotify API, got access to playlists, read doumentation
1 | 2023-08-04 | Spotify API - fetch songs | 3 | n/a | Yes | Was able to fetch songs from a specified playlist
1 | 2023-08-05 | Spotify API - fetch song data | 2 | n/a | Yes | Filtered out song data/artist information from all API output data
1 | 2023-08-06 | Python Logic - pygame, tkinter | 6 | n/a | Yes | Coded python logic for version1 of the game where a song played and the user had to input the artist name to score points
Erin was the scrum master this week:
1 | 2023-08-07 | Group meeting | 0.5 | All | Yes | Update on what we did week before, set our own tasks for the next week
| 2023-08-08 | Group Homework | 0.5 | n/a | Yes | Completed allocated Group Homework Question 2
| 2023-08-08 | Research - Kivy & turning a python program into an android game with google | 2 | n/a | Yes | Read google articles and watches youtube tutorials on kivy. Tried some basic kivy code
| 2023-08-09 | Python Logic - Quiz style options | 1.5 | n/a | Yes | Changed python logic to provide artist options. Added start game, option and end game buttons with kivy
2 | 2023-08-09 | Suggested source tree directory | 0.5 | n/a | Yes | Read about source tree directory and suggested we separate the code into 4 folders game_logic, ui, database and resources
2 | 2023-08-09 | Initial game design, system requirements and architecture | 0.5 | n/a | Yes | Created game design and system architecture for project - used as a framwork for answering the group homework
2 | 2023-08-10 | Removed some bugs & uploaded initial version of the game onto github | 2 | n/a | Yes/No | There were still afew glitches in the game
2 | 2023-08-10 | Reviewed complete group homework file | 3 | n/a | Yes | Corrected inconsistencies and mistakes. Added missing bits. Messaged the group to review the edits before handing it in
2 | 2023-08-11 | Handed in the homework | 0.3 | n/a | Yes | submitted the homework to Becky and Sophia. Later in the day sent a copy to Niroshan as requested on the software 3 channel
2 | 2023-08-12 | Python Logic - glitches | 2 | n/a | Yes | FIxed issue with songs randomly skipping and song play time
2 | 2023-08-13 | Planning for the week ahead & CFG project specifications | 1 | n/a | Yes | Looked through CFG specifications and make a list of tasks to be completed
I (Parineeta) was the scrum master for this week:
3 | 2023-08-14 | Group meeting - Assigned tasks as planned on the 13/08/2023 | 0.75 | All | Yes | Took over from Erin, discussed what needs to be done this week. Assigned tasks, checked if anyone needed any help. Updated the Kanban board
3 | 2023-08-16 | Research how to test kivy code | 2 | n/a | No | Tried some code but it did not work. Need to expand my kivy knowledge. Use user acceptance testing as the deadline is nearing
3 | 2023-08-19 | Refactored code into game_logic, ui and resources | 4 | n/a | Yes | created new directories to add files into
3 | 2023-08-20 | Wrote 6 unsuccessful - mock tests? | 2 | n/a | No | Its hard to test games
Sarah was the scrum master this week:
3 | 2023-08-21 | Group Meeting | 1.5 | n/a | Yes | Handed over task list to this weeks Scrum Master -Sarah. Updated team with work done and set this weeks tasks
3 | 2023-08-21 | Quick meeting to update Erin | 0.3 | n/a | Yes | Updated Erin on what she missed in todays group meeting
4 | 2023-08-22 | Group meeting | 0.75 | n/a | Yes | Listed to dos to complete the project, split up tasks
4 | 2023-08-22 | Wrote 4 successful unit tests | 2 | n/a | Yes | 3 unit tests for the song data file and 1 for the spotify api
4 | 2023-08-23 | Group meeting | 0.75 | All, except Natalie (work) | Yes | Listed to dos to complete the project, split up tasks
4 | 2023-08-24 | Dealing with import errors - nothing would work?! | 2 | n/a | No/Yes | It did not work initially but then started working after I re-configured the interpreters (I dont know how/why it started working)
4 | 2023-08-24 | Afterclass help with imports from - Kenny | 0.5 | Eliza, Sarah, Kenny | Yes/No | It worked for a bit and then showed the same errors
4 | 2023-08-25 | Add image file with kivy | 0.5 | n/a | Yes | Managed to add a .jpg onto our game!
4 | 2023-08-25 | Group meeting - Clean up github main branch, work on scoreboard database connection | 3 | Eliza, Erin, Sarah | Yes/No | Cleaned up github main branch
4 | 2023-08-26 | Showed games to friends and family | 0.5 | n/a | Yes | We now have some user acceptance feedback!
4 | 2023-08-26 | Documentation, trying to split kivy code from python, trying to use sqlite3 | 8 | n/a | No/Yes | Yes for the documentation. Could not successfully split off into .kv files need to work on my kivy skills. Tried to create a simple database file in our project with username and scores but it would crash the whole game. Need to research sqlite3
4 | 2023-08-27 | Reviewed complete project report, code files & github repo | 8 | n/a | Yes | Proof-read the complete group report
4 | 2023-08-27 | Group Meeting - Submit Project & Presentation | 0.5 | All | Yes | Submit Project & Discuss Presentation
|  | Total time: | 76.35